## Metadata
Page Title | Edgecore SONiC Release ETA in 2025
Total Tables | 1
Generated At | 2025-07-14 13:35:35

## Table_1
Version | Month | Release ETA | Release Contents | Status
202211.4 | 2024-12 | 12/06 (CA 11/21) | (New Features) Cut-through mode. | Released
202311.1 | 2024-12 | 12/27 (CA 12/12) | All platforms and features supported in current Community 2311, EC SONiC 2111, and EC SONiC 2211 Release. SAI: EC SAI-1.13 (1.0.0) New Platforms: VM (init) | Released
202211.4.2 | 2025-01 | 01/10 | Release for SAKURA & BeyondEdge. Issue Fixes: SONIC-11280, SONIC-11313. | Released
SAI 1.13 for AIS800-32 | 2025-01 | 01/17 (CA 01/10) | Release for eBay.
NEP | 2025-02 | 02/21 02/27 | Platforms: 9726-32DB Features: PTP Boundary Clock & Multicast Enabling. | Released
202211.5 | 2025-02 | 02/14 (CA 01/23) 02/25 (CA 02/13) 03/14 -> 03/26 | Enhancements: ECN Counter on TH4 (Evollabs 2111) sFlow Drop Notification on TH5 DLB on TD4 (APS/ KDDI AI Fabric) Enhance tech-support dump to monitor/collect system resource (CPU/Memory) for debugging hang issues ( SAKURA ). | Released
202311.2 | 2025-03 | 03/07 (CA 02/20) 04/08 | Known issue fix ETA update for sonic-mgmt old TCs: 01/08. Final sonic-mgmt TCs submission: 02/13. Complete the feature supports on all platforms (feasible but not yet supported in 2111/2211) ECN Counter Marking PFC Watchdog Dead Lock Restoration Mechanism Cut-through Mode sFlow Drop Notification DCBx NAC: 802.1x, CoA, MAB New Features: Load Balance: LAG/ECMP Hash Options Tagged Mgmt Port Enhancements: Configurable CoPP IGMP Snooping isCLI (draft) Static DNS Server Configuration New Platforms AIS800-32D/O (SDK need to upgrade to 6.5.32) => Thermal plan → PLM (?) VM (verified with test cases) | Released
202111.10.2 | 2025-03 | 03/26 | Patch Release for Karl Storz (#37430). Patch Release for STORIS/RTB House (#40598). | Released
202211.5.1 | 2025-04 | 04/12 | Patch Release for Evollabs (#41467 & #41367) | Released
202411.0 | 2025-04 | 03/31 (Priority-1) 04/30 (Priority-2) | Enable Community 202411 on platform(s), refer 202311.0 (inner) Customers requiring 2411.0: AFC: AS4625-54P (TBD), AS4630-54PE, AS5835-54X Nexthop: AIS800-64D/O, AS7712-32X, AS5835-54X => (2025.02.27, William) DCS201(AS5835-54T), DCS204(AS7726-32X) US Gov FIPS 140-3: AS7726-32X Bloomberg: AIS800-64D, AIS800-32D Priority-1 Platforms: AIS800-64D/O, AS4630-54PE/TE, AS5835-54X, AS7726-32X. Priority-2 Platforms: AIS800-32D/O, AS4625-54P/T, AS4630-54NPE, AS5835-54T, AS7326-56X, AS7712-32X, AS7816-64X, AS9716-32D, AS9726-32DB, AS9736-64D, AS9737-32DB. EC SAI 1.15 - preparing EC SAI for 2411.X and resolving the critical issues caused by community SAI in case the customer has concerns. Release 2411.0 with EC SAI 1.15 supported on AS4630-54PE & AS5835-54X for AFC on 03/31. | Released
202211.5.2 (for Nous) | 2025-04 | 04/24 (CA 04/17) | Fix all SIT issues submitted from TCs related to Nous demo. Decided to use the 202211 build #613 for the first-stage demo before 202311.X is ready. This build will be assigned the version number 202211.5.2. | Released
202111.11 | 2025-04 | 04/25 (CA 04/10) | (New Features) RPVST/PVST over MCLAG. (Req: Sharp , RFP) SOLTEC wants MSTP over MCLAG (checking if they can adopt RPVST or not). ECN Counter ( Evollabs ) In-band Mgmt ( MediaTek & Novatek - customers of immersion cooling). SSH Timeout ( Telecentras ). TBRH-536, ACL inport, outport on AS5835-54T (Req: Apreasia, NTT-PC ) isCLI v1.3 ( Apresia ) | Released
202211.5.1.1 | 2025-04 | 04/30 | Patch release for Evollabs (issue fixes & enhancement: #41367, ##41467, #42001). | Released
202211.5.1.2 | 2025-05 | 05/16 | Patch release for Netris/TensorWave (issue fixes: #40782 & #42368). | Released
202311.X | 2025-05 | CA: 04/30 05/15 06/05 07/03 07/17 Release: 05/16 05/23 07/11 07/25 |  | Required Features: Required Platforms: AS7326-56X, AS7726-32X, AS9726-32DB, AS9736-64D, AS9737-32DB, AIS800-32D/O, AIS800-64D/O. Community SAI cannot support the following platforms: AIS800-32D/O: SDK version inside community SAI has not yet supported this TH5 switch ASIC. AS9737-32DB: SDK version inside community SAI has not yet supported this TH4 switch ASIC. AS9726-32DB: critical FDB issues have been identified in the current community SAI on TD4.
202211.5.3 | 2025-05 | 05/26 | Patch release for SAKURA and plan to support CPU watchdog on AIS800. | Released
202311.3 | 2025-06 | 06/06 (CA 05/22) 06/27 (CA 06/12) | For KDDI /Kynos Migration from 2111. Apresia request to verify two previous issues: #33840 , #33327 Platforms: AS7712-32X, AS7816-64X. New Features: Interface Naming (TBRH-381) FIPS 140-3 (TBRH-486) => push out to 202411.0 UDF Hashing (delay to 2311.4) => :question_mark: Configurable IPv6 Link Local Migration of Existing Features Object Track MC-LAG xSTP LLDP-MED (PoE) (delay to 2311.4) RESTAPI (might not be fully ready in 2311.3, updated on 05/13) isCLI (might not be fully ready in 2311.3, updated on 05/13) VRRP DLB Protocol Down | Released
202311.3.1 | 2025-06 | 06/27 | Patch release for MACNICA/SOLTEC to solve 9726 PSU fan direction issue. | Released
202211.5.4 | 2025-06 | 06/25 | Patch release for Netris/TensorWave (SONIC-12573).
202211.5.5 | 2025-07 | 07/04 | Patch release for Netris/TensorWave (SONIC-11765, SONIC-12607, SONIC-12577, SONIC-12622, JRTC-24951).
202411.X ( cancel ) | 2025-06 | 06/27 (CA 06/12) | (updated on 05/21 - plan to cancel 2411.X and 2411.N due to the changes in SONiC product strategy) Xsight, enable X2 device (common feature) Link Training Auto-negotiation Mirroring (SPAIN, ERSPAN, Ever flow) FDB LAG (LACP) LLDP VLAN ARP BGP ECMP VRP BFD ACL PFC ECN Scheduling DHCP relay SNMP Telemetry ZTP
202211.6 | 2025-08 | 08/15 (CA 07/31) | Customer issue fixes only.
202311.4 | 2025-09 | 09/05 (CA 08/21) | KDDI POC starts from Oct’25 after we verify all known tickets.( MEI.APS.KDDI.Kyanos. - ecSONiC Collaboration - Confluence ) New Features: FIB Pending Suppression UDF Hashing Extended Hash Field for RDMA Fine-Grained ECMP (TBD) xSTP over MC-LAG (TBD) Loop detection over IP fabric (TBD) Static VxLAN :question_mark: => Cancel, Gord cannot commit. Port mirroring to remote Leaf (VTEP) (TBD) isCLI v1.4 MCLAG supported on VS Locator LED Banner OSPFv3 ECMP Resource Optimization for MH Asymmetric Route
202411.1 ( cancel ) | 2025-09 | 09/26 (CA 09/11) | (updated on 05/21 - plan to cancel 2411.X and 2411.N due to the changes in SONiC product strategy) 802.1X, MAB SAG PVST/RPVST BPDU Guard IPSG, SAI, DHCPSNP VLAN stacking (QinQ) DLB EVPN/VxLAN EVPN-MH OSPF/ISIS RoCEv2 (lossless) 802.3(PoE), manually configure PoE static FDB hardware reset TDR (cable diagnostic) flow control, (802.3X global pause) telemetry (gNMI, gRPC) SAI: ecSAI-1.15 (V1.0.0)
202111.12 | 2025-11 | 11/14 (CA 10/30)